| FORGE FORGEDBYARIS.COM | Contractor Outreach Checklist Find, Vet, Hire & Close Out |
| --- | --- |

This checklist walks you through every step of building your contractor team — from creating your credibility packet through final payment and project closeout. Work through each phase in order. Check off each item as completed.

PHASE 1 — BUILD YOUR CONTRACTOR CREDIBILITY PACKET

|  | Task | Description / Notes |
| --- | --- | --- |
| ☐ | Company Background | Write a professional company overview. Introduce your business, your market, and your track record. This is your first impression — make it serious and credible. |
| ☐ | Short & Long Term Goals | Show contractors you have a pipeline. Outline your renovation targets for this year and your 3-5 year vision. Contractors want consistent work, not one-off jobs. |
| ☐ | Why You're Good to Work With | List your differentiators: you pay on time, provide detailed scopes of work, offer repeat business, and treat contractors like partners — not just vendors. |
| ☐ | Your Ideal Contractor Profile | Define the characteristics, trades, and standards you're looking for. Mention the high potential for long-term, repeat business if your standards are met. |
| ☐ | Contractor Requirements | State your minimum licensing, insurance, and warranty requirements clearly. This pre-filters unqualified contractors before you invest time in them. |
| ☐ | How You Administer Projects | Include a sample scope of work, your draw schedule structure, and your change order process. Show contractors you run a professional, documented operation. |

PHASE 2 — PRESCREEN THE CONTRACTOR

|  | Task | Description / Notes |
| --- | --- | --- |
| ☐ | Contractor Application | Have every candidate complete the full Contractor Application before your first meeting. Use FORGE-Contractor-Application.docx. |
| ☐ | Contractor's License | Obtain a copy of the contractor's license. Verify it is active and in good standing through your state licensing board or local municipality. |
| ☐ | Workers' Compensation | Obtain a copy of workers' compensation insurance if the contractor has employees. This protects you from liability for on-site injuries. |
| ☐ | Liability Insurance | Obtain a current certificate of liability insurance. Minimum coverage: $1,000,000 per occurrence. You should be named as additionally insured on active projects. |
| ☐ | EPA Certification | If your property was built before 1978, the contractor must hold an EPA Lead-Safe Certified Renovator certification. Obtain a copy. |
| ☐ | Conduct the Interview | Use the FORGE-Contractor-Interview-Sheet.docx to run a structured interview. Cover similar past projects, management style, timing, bidding process, and conflict resolution. |
| ☐ | Reference Check | Contact all provided references using the FORGE-Contractor-Reference-Check-Sheet.docx. Document all answers for your records. |
| ☐ | Create a Contractor File | Open a digital folder for this contractor. Store all documents: license, insurance, EPA cert, application, references, and notes. |

PHASE 3 — HIRE THE CONTRACTOR

|  | Task | Description / Notes |
| --- | --- | --- |
| ☐ | Award the Project | Notify the contractor they've been selected. Schedule a job site walkthrough and final scope review meeting. |
| ☐ | Review the Draw Schedule | Walk through your payment schedule together. Confirm each draw milestone, the inspection process, and the timeline for payment release after approval. |
| ☐ | Execute the Six Critical Documents | Do NOT start any work until all six documents are signed. Do NOT sign documents before you have closed on the property. The six documents are: (1) Contractor Agreement, (2) Scope of Work, (3) Draw Schedule, (4) Lien Waiver, (5) W-9, (6) Certificate of Insurance naming you as additional insured. |
| ☐ | Project Kickoff | Confirm start date, site access, material delivery schedule, and daily check-in protocol. Reference FORGE-Short-Sale-Due-Diligence-Sheet for property condition baseline. |

PHASE 4 — PROJECT EXECUTION (ONGOING)

|  | Task | Description / Notes |
| --- | --- | --- |
| ☐ | Daily Check-Ins | Require daily progress updates from the GC — photos, status, and any issues. Respond within same business day. |
| ☐ | Milestone Inspections | Inspect and approve each draw milestone before releasing payment. Document with photos and written sign-off. |
| ☐ | Change Order Management | Any scope changes must be submitted as written change orders before work begins. No verbal approvals. No retroactive change orders. |
| ☐ | Permit Management | Confirm all required permits are pulled by the contractor before work begins. Inspect permit cards are posted on site. |

PHASE 5 — CONTRACT CLOSEOUT & FINAL PAYMENT

|  | Task | Description / Notes |
| --- | --- | --- |
| ☐ | Final Walkthrough & Punch List | Walk the entire property with the GC. Document every item not completed to standard. Provide the punch list in writing before issuing any final payment. |
| ☐ | Confirm Punch List Completion | Re-inspect every punch list item after the contractor reports completion. Do not issue final payment until all items are verified. |
| ☐ | Schedule Final Inspections | Final inspections are scheduled by the contractor and close out all open permits. Confirm inspection dates and obtain copies of all passing inspection reports. |
| ☐ | Certificate of Occupancy | Obtain the Certificate of Occupancy from the Building Department once all inspections pass. Required for sale or rental in most jurisdictions. |
| ☐ | Final & Unconditional Lien Waiver | Do NOT issue final payment until the contractor has signed the Final & Unconditional Waiver of Lien. This protects you from future lien claims. |
| ☐ | Release Final Payment | Issue final payment immediately after the signed lien waiver is in hand. Do not delay — prompt payment builds the relationship for future projects. |

PHASE 6 — POST-PROJECT FILE MANAGEMENT

Keep all of the following documents together in a single project folder (digital and/or physical):

- Six Critical Documents (signed copies)

- Scope of Work — original and all approved change orders

- All contractor estimates and bids received

- Architectural drawings and permits

- Copies of all executed contracts

- Change order documentation with written approvals

- All correspondence with contractor and subcontractors

- Record of all draw payments with dates and amounts

- All invoices received (retain for tax purposes)

- Inspection reports and Certificate of Occupancy

- Final lien waiver — signed and dated

- Before and after photos of the project

FORGE  |  Powered by ARIS  |  ForgedByAris.com