| FORGE FORGEDBYARIS.COM | Rehab Project Management Checklist Pre-Rehab Through Final Punch List |
| --- | --- |

PRE-REHAB — PLANNING & SETUP

| ✓ | ACTION ITEM | DESCRIPTION / NOTES |
| --- | --- | --- |
| ☐ | Final Property Walkthrough | Walk the property a second time and spend more time identifying any repair items missed in the initial repair estimate. Flag anything that requires a specialist or professional investigation before finalizing your Scope of Work. |
| ☐ | Review SOW Materials Library | Review your materials library to select finishes, fixtures, and materials for the property. Add all selections to the Scope of Work so contractors are bidding the same specifications. |
| ☐ | Write Detailed Scope of Work (SOW) | Write a room-by-room, line-by-line Scope of Work. Use your SOW Writing Checklist to ensure nothing is missed. The SOW is the single most important document in your rehab — every contractor bids from it. |
| ☐ | Find Contractors to Bid the Project | Use your Contractor Marketing Checklist to identify and recruit qualified contractors for each trade. Minimum 3 bids per major trade. |
| ☐ | Send Contractors the SOW for Bidding | Provide all bidding contractors with the property access information and the full Scope of Work so they can walk the property and submit accurate bids. |
| ☐ | Review All Bids for Accuracy | Review all incoming bids to confirm each contractor is bidding the same scope. Misaligned bids — where one contractor includes work another excludes — produce misleading price comparisons. |
| ☐ | Select Best Bids for Negotiation | Identify the contractors with the most accurate and competitive bids. Do not automatically select the lowest bid — evaluate experience, references, and timeline as well. |
| ☐ | Negotiate Contractors | Work with your top candidates to determine their best price without changing the scope. Be direct about your budget and timeline. Good contractors will negotiate — great contractors will meet you in the middle. |
| ☐ | Select Final Contractors | Make your final contractor selections for all trades. Confirm start date availability and project timeline before committing. |
| ☐ | Execute 6 Critical Documents | Before any contractor begins work, execute all 6 Critical Documents: Independent Contractor Agreement, Insurance Indemnification Form, Scope of Work, W-9, Payment Schedule, and Final Lien Waiver (to be signed upon completion). |
| ☐ | Receive Back All Signed Documents | Confirm all 6 Critical Documents are returned fully signed and correctly filled out before work begins. Do not allow any contractor on site without completed paperwork. |
| ☐ | Receive Insurance Certificates | Collect a Certificate of Insurance from every contractor listing [YOUR COMPANY] as additionally insured. Verify coverage amounts meet your minimum requirements before work begins. |
| ☐ | Set Rehab Start Date | Coordinate with all contractors to establish a project start date that aligns with property closing. Confirm the schedule in writing with each trade. |
| ☐ | Pull Construction Permit | Have your contractor or architect pull the required construction permit at the local building department before any work begins. Unpermitted work creates title and liability issues at resale. |

DURING CONSTRUCTION — PHASE MILESTONES

| ✓ | ACTION ITEM | DESCRIPTION / NOTES |
| --- | --- | --- |
| ☐ | Kick-Off Meeting | Meet with all contractors and subcontractors at the property on day one. Distribute a contact sheet with every trade's name, phone, and scope. Set communication expectations and weekly check-in schedule. |
| ☐ | Demo & Cleanout Complete | Confirm all demolition per the SOW is complete. All debris and trash must be removed before framing and rough work begins. A clean jobsite is a safer and more efficient jobsite. |
| ☐ | Underground Work | Inspect all underground work — plumbing, electrical, and any foundation rebar — before covering. This includes any work that will be buried under dirt or concrete. Must pass city inspection before cover. |
| ☐ | Underground Inspection Passed | Contractor must call the city to schedule a building inspector for all underground work before covering. Do not allow work to proceed until inspection is passed and documented. |
| ☐ | Framing Rough Out | Inspect all framing work — floor system, wall framing, and roof structure — as construction progresses. Start from the floor system and work up. Multiple city inspections may apply depending on scope. |
| ☐ | Mechanicals Rough Out | Inspect all rough mechanical work — electrical, plumbing, and HVAC — before walls are closed. Refer to your Rough Inspection Checklist for each trade. |
| ☐ | New Roof Installed | Confirm the roofing contractor has completed the roof per the SOW specifications — correct material, color, and installation method. All prior inspections must be passed before roof goes on. |
| ☐ | Rough Inspection Passed | Call the city for a rough framing, electrical, plumbing, and HVAC inspection before insulation is installed. No drywall until rough inspection is passed and documented. |
| ☐ | Insulation Installed | Confirm insulation is installed in all required areas per building code and your SOW. Proper insulation is required for energy compliance and a passing final inspection. |
| ☐ | Insulation Inspection Passed | Call the city for an insulation inspection before drywall is hung. Required in most jurisdictions. |
| ☐ | Drywall Hung | Hanging only at this phase — no taping or texturing yet. Inspect for correct screw pattern and coverage before calling for inspection. |
| ☐ | Drywall Inspection Passed | Call the city for a drywall inspection. Inspector verifies screw spacing and pattern. Pass before proceeding to tape and texture. |
| ☐ | Exterior Lath Installed | Install exterior waterproofing layer before applying the final exterior coating. Required for stucco and most siding systems. May not apply depending on your exterior finish type. |
| ☐ | Exterior Lath Inspection Passed | Call the city for exterior lath inspection before applying the exterior finish coating. |
| ☐ | Interior Lath / Waterproofing Installed | Install waterproofing membrane in all shower surrounds before tile work begins. Required for any wet area. |
| ☐ | Interior Lath Inspection Passed | Call the city for interior lath inspection before tile installation begins in wet areas. |
| ☐ | Paint Interior & Exterior | Confirm paint colors match the SOW specifications. Inspect coverage and finish quality before signing off. Touch-up phase happens at punch list. |
| ☐ | Flooring & Tile Installed | Confirm the correct flooring type is installed in the correct locations per the SOW. Verify tile pattern and grout color match specifications. |
| ☐ | Kitchen Cabinets Installed | Confirm cabinets are the correct style, color, and configuration per the SOW. Inspect layout, alignment, and hardware placement before countertop templating. |
| ☐ | Shower Tile Installed | Confirm correct tile is installed in all shower surrounds per the SOW. Inspect pattern, grout lines, and waterproofing seams. |
| ☐ | Landscaping Started | Send landscaping contractor to begin demo and install. Walk the contractor through the full landscape plan to confirm scope, plant selections, and budget alignment before work begins. |
| ☐ | Bath Vanities Installed | Confirm vanities are the correct style and installed in the correct locations per the SOW. Inspect plumbing connections before signing off. |
| ☐ | Countertops / Granite Installed | Confirm plywood sub-tops are installed before granite templating. After installation, confirm correct material, edge profile, and color per SOW. |
| ☐ | Mechanical Trim Out | Electrical trim — install all switches, outlets, and cover plates. HVAC trim — install all registers, thermostats, and grilles. Plumbing trim — install all fixtures and shutoffs. |
| ☐ | Bath Accessories Installed | Confirm all bathroom accessories are installed in the correct locations — toilet paper holder, hand towel holder, bath towel bar, robe hooks, and mirror. |
| ☐ | Appliances Installed | Confirm all appliances are the correct make, model, and finish per the SOW. Inspect for damage from delivery or installation. |
| ☐ | Landscaping Completed | Walk the finished landscaping with the contractor. Confirm all plant material, irrigation, bark, and lawn areas are complete and match the original plan. Begin landscape maintenance schedule. |
| ☐ | Final Cleaning Complete | Post-construction deep clean performed by a professional cleaning crew. All contractor debris removed. Unit must be showroom-ready before final inspection. |
| ☐ | Final City Inspection Passed | Call the city for final inspection. All permitted work must pass final inspection before the property can be legally occupied or sold. Document the signed permit card. |
| ☐ | Punch List Completed | Complete a full punch list walkthrough using your FORGE Rehab Punch List Checklist. Walk line by line with the contractor and sign off on each item before releasing final payment. |
| ☐ | Punch List Verified & Signed Off | Walk the property a final time with the contractor to verify every punch list item is resolved. Both parties sign off. Final payment and lien waivers exchanged upon completion. |

FORGE  |  Powered by ARIS  |  ForgedByAris.com